## v1
Task | Start Date | Duration (Days) | End Date | Custom Dates | Milestone Data |  | Task Order
Início das reuniões de acompanhamento | 2025-02-10 | 0 | 2025-02-10 | 10-fev | 10/02/2025 | 45698 | 1 | 1
Website Development | 2025-02-10 | 21 | 2025-03-03 | 10-fev ↔ 03-mar |  | #VALUE! | 2 | 2
Search for articles about our project | 2025-02-11 | 6 | 2025-02-17 | 11-fev ↔ 17-fev |  | #VALUE! | 3 | 3
Project Proposal Powerpoint improvements | 2025-02-12 | 12 | 2025-02-24 | 12-fev ↔ 24-fev |  | #VALUE! | 4 | 4
Pre-testing with a simplified prototype | 2025-02-17 | 35 | 2025-03-24 | 17-fev ↔ 24-mar |  | #VALUE! | 5 | 5
Components materials market search | 2025-02-18 | 15 | 2025-03-05 | 18-fev ↔ 05-mar |  | #VALUE! | 6 | 6
Schedule and start interviewing | 2025-02-19 | 24 | 2025-03-15 | 19-fev ↔ 15-mar |  | #VALUE! | 7 | 7
Plataform for team management creation | 2025-02-20 | 2 | 2025-02-22 | 20-fev ↔ 22-fev |  | #VALUE! | 8 | 8
Entrega da proposta de projeto revista | 2025-02-24 | 0 | 2025-02-24 | 24-fev | 24/02/2025 | 45712 | 9.5 | 9
Lançamento do website+blog | 2025-03-03 | 0 | 2025-03-03 | 03-mar | 03/03/2025 | 45719 | 10.5 | 10
Website maintenance and updating | 2025-03-03 | 124 | 2025-07-05 | 03-mar ↔ 05-jul |  | #VALUE! | 11 | 11
Elaboração da lista de requisitos para o protótipo | 2025-03-17 | 5 | 2025-03-22 | 17-mar ↔ 22-mar |  | #VALUE! | 12 | 12
Elaboração da lista de materiais para o protótipo | 2025-03-24 | 5 | 2025-03-29 | 24-mar ↔ 29-mar |  | #VALUE! | 13 | 13
Prototype assembly | 2025-03-25 | 10 | 2025-04-04 | 25-mar ↔ 04-abr |  | #VALUE! | 14 | 14
Protoype Basic Testing | 2025-04-01 | 3 | 2025-04-04 | 01-abr ↔ 04-abr |  | #VALUE! | 15 | 15
Prototype Full Testing and adjustments | 2025-04-04 | 59 | 2025-06-02 | 04-abr ↔ 02-jun |  | #VALUE! | 16 | 16
Submissão da versão provisória da apresentação intermédia | 2025-04-07 | 0 | 2025-04-07 | 07-abr | 07/04/2025 | 45754 | 17.5 | 17
Data limite para a submissão da versão final da apresentação intermédia | 2025-04-14 | 0 | 2025-04-14 | 14-abr | 14/04/2025 | 45761 | 18.5 | 18
Video making | 2025-03-24 | 78 | 2025-06-10 | 24-mar ↔ 10-jun |  | #VALUE! | 19 | 19
Disponibilidade da primeira versão do protótipo para o início da fase de testes | 2025-05-26 | 0 | 2025-05-26 | 26-mai | 26/05/2025 | 45803 | 20.5 | 20
Fase de testes do protótipo | 2025-05-26 | 7 | 2025-06-02 | 26-mai ↔ 02-jun |  | #VALUE! | 21 | 21
Poster making | 2025-06-01 | 3 | 2025-06-04 | 01-jun ↔ 04-jun |  | #VALUE! | 22 | 22
Conclusão do protótipo e dos seus testes | 2025-06-02 | 13 | 2025-06-15 | 02-jun ↔ 15-jun |  | #VALUE! | 23 | 23
Eletro Day speech and demostration preparation | 2025-06-04 | 31 | 2025-07-05 | 04-jun ↔ 05-jul |  | #VALUE! | 24 | 24
Elaboração dos materiais de comunicação | 2025-06-09 | 0 | 2025-06-09 | 09-jun | 09/06/2025 | 45817 | 25.5 | 25
Data limite para a submissão dos materiais de avaliação | 2025-06-16 | 0 | 2025-06-16 | 16-jun | 16/06/2025 | 45824 | 26.5 | 26
ElectroDay | 2025-07-05 | 0 | 2025-07-05 | 05-jul | 05/07/2025 | 45843 | 27.5 | 27
Formulas:
End Date = [Start Date]+[Duration (Days)]

## v2
Task | Start Date | Duration (Days) | End Date | Custom Dates | Milestone Data |  | Task Order
Início das reuniões de acompanhamento | 2025-02-10 | 0 | 2025-02-10 | 10-fev | 10/02/2025 | 45698 | 1 | 1
Website Development | 2025-02-10 | 21 | 2025-03-03 | 10-fev ↔ 03-mar |  | #VALUE! | 2 | 2
Search for articles about our project | 2025-02-11 | 6 | 2025-02-17 | 11-fev ↔ 17-fev |  | #VALUE! | 3 | 3
Project Proposal Powerpoint improvements | 2025-02-12 | 59 | 2025-04-12 | 12-fev ↔ 12-abr |  | #VALUE! | 4 | 4
Pre-testing with a simplified prototype | 2025-02-17 | 70 | 2025-04-28 | 17-fev ↔ 28-abr |  | #VALUE! | 5 | 5
Components materials market search | 2025-02-18 | 34 | 2025-03-24 | 18-fev ↔ 24-mar |  | #VALUE! | 6 | 6
Interviewing | 2025-02-19 | 53 | 2025-04-13 | 19-fev ↔ 13-abr |  | #VALUE! | 7 | 7
Plataform for team management creation | 2025-02-20 | 2 | 2025-02-22 | 20-fev ↔ 22-fev |  | #VALUE! | 8 | 8
Entrega da proposta de projeto revista | 2025-02-24 | 0 | 2025-02-24 | 24-fev | 24/02/2025 | 45712 | 9.5 | 9
Lançamento do website+blog | 2025-03-03 | 0 | 2025-03-03 | 03-mar | 03/03/2025 | 45719 | 10.5 | 10
Website maintenance and updating | 2025-03-03 | 124 | 2025-07-05 | 03-mar ↔ 05-jul |  | #VALUE! | 11 | 11
Elaboração da lista de materiais para o protótipo | 2025-03-18 | 6 | 2025-03-24 | 18-mar ↔ 24-mar |  | #VALUE! | 12 | 12
Simulations Elaboration | 2025-04-21 | 20 | 2025-05-11 | 21-abr ↔ 11-mai |  | #VALUE! | 13 | 13
Prototype assembly | 2025-04-28 | 7 | 2025-05-05 | 28-abr ↔ 05-mai |  | #VALUE! | 14 | 14
Protoype Basic Testing | 2025-05-05 | 5 | 2025-05-10 | 05-mai ↔ 10-mai |  | #VALUE! | 15 | 15
Prototype Full Testing and adjustments | 2025-05-10 | 16 | 2025-05-26 | 10-mai ↔ 26-mai |  | #VALUE! | 16 | 16
Submissão da versão provisória da apresentação intermédia | 2025-04-08 | 0 | 2025-04-08 | 08-abr | 08/04/2025 | 45755 | 17.5 | 17
Submissão da versão final da apresentação intermédia | 2025-04-14 | 0 | 2025-04-14 | 14-abr | 14/04/2025 | 45761 | 18.5 | 18
Video making | 2025-05-05 | 36 | 2025-06-10 | 05-mai ↔ 10-jun |  | #VALUE! | 19 | 19
Primeira versão do protótipo | 2025-05-26 | 0 | 2025-05-26 | 26-mai | 26/05/2025 | 45803 | 20.5 | 20
Fase de testes do protótipo | 2025-05-26 | 20 | 2025-06-15 | 26-mai ↔ 15-jun |  | #VALUE! | 21 | 21
Poster making | 2025-06-01 | 5 | 2025-06-06 | 01-jun ↔ 06-jun |  | #VALUE! | 22 | 22
Eletro Day speech and demostration preparation | 2025-06-04 | 31 | 2025-07-05 | 04-jun ↔ 05-jul |  | #VALUE! | 23 | 23
Elaboração dos materiais de comunicação | 2025-06-09 | 0 | 2025-06-09 | 09-jun | 09/06/2025 | 45817 | 24.5 | 24
Submissão dos materiais de avaliação | 2025-06-16 | 0 | 2025-06-16 | 16-jun | 16/06/2025 | 45824 | 25.5 | 25
ElectroDay | 2025-07-05 | 0 | 2025-07-05 | 05-jul | 05/07/2025 | 45843 | 26.5 | 26
Formulas:
End Date = [Start Date]+[Duration (Days)]